## GanttChart
Project Schedule |  |  |  | Urgent Items
Hulse Research Lab
| Project Start Date : | 2021-08-16 | [6 empty] | Display Week | 23 | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30
[11 empty] | 2022-01-17 | [6 empty] | 2022-01-24 | [6 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07
 | time axis 2022-01-17 to 2022-03-13
WBS | TASK | EQUIPMENT / SOFTWARE | CODE FILE NAME | CODE FILE LOCATION | CODE UPDATES / NOTES | ToDo | START | END | DAYS | time axis 2022-01-17 to 2022-03-13
1 | Dod_Evan
1 | Signal Sequencer File & Code | Signal, Spike, 1401, Grass | Pulse_5 | DoD_Evan Folder Github | Code can run a train of 5 pulses with .5 seconds apart with a manual trigger IMP: Set Grass to Function S1 Delay for the system to work |  | 2021-08-26 | 2021-09-01 | 6
1.1 | Signal Sequencer File & Code | Signal, Spike, 1401, Grass | Pulse_5 | DoD_Evan Folder Github | Update Code such that pulse is 1ms, seperated by 1ms for 20 ms, therefore 20 ms active pulses each at 500 Hz Visual of Train set up in documents dod_evan |  | 2021-09-03 | 2021-09-09 | 6
1.2 | Signal Sequencer File & Code | Signal, Spike, 1401, Grass | Pulse_Train | DoD_Evan Folder Github | Created by configuration panel | Was not the sequencer code, GRASS x10 needs to be turned to x1 - manageable pulse after this adjustment | 2021-09-09 | 2021-09-13 | 4
1.3 | Thenar Muscle Values MEP | MATLAB | MEP_Value_Pull Plots_3 ; Only 3 consecutive Plots_5; Only 5 consecutive | DoD_Evan | Issues with file not having correct values, the problem might have been getting the files mixed up MEP Value Pull only contains changes associated with the if statements [lines 101,116,129,144] | Files sent to Evan on 9/27 | 2021-09-27 | 2021-09-27 | 0
1.4 | Thenar Muscles MEP Value Pull | MATLAB | MEP Value Pull | DoD_Evan | Needs variation for finding Onset and Off set | Create several different code file versions including 3 On 3 Off x2 5 On 5 Off x2 3/5 On 3 Off x2 3 On 3/5 Off x2 As well as area under 2 curves and area from onset 1 to offset 2 | 2021-09-28 | 2021-10-04 | 6
1.5 | Thenar Muscles MEP Value Pull | MATLAB | MEP Value Pull (Method 1-2) MEP_Value_Pull_Method_3_4 | DoD_Evan | Files: Data_Method_1-4 contain excel files of all values requested | Send the file to Evan next week | 2021-10-01 | 2021-10-04 | 3
1.6 | Thenar Muscles MEP Value Pull | MATLAB | MEP Value Pull (Method 1-2) MEP_Value_Pull_Method_3_4 | DoD_Evan | Code updated such that B starts over at 0 when loop of f = 5 is completed | Issues with Code method 3 - identification of offset flagged as false on P11 _ Go through the Method 3 code - determined that iterations was the issue | 2021-10-13 | 2021-10-14 | 1
1.7 | Thenar Muscles MEP Value Pull | MATLAB | MEP_Value_Pull_Method_3_4 | DoD_Evan | Reporting issue - needs to report the first number in the 3/5 series | Just replaced f with i in the reporting after B>=3 | 2021-10-19 | 2021-10-20 | 1
1.8 | Thenar Muscles MEP Value Pull | MATLAB | MEP_Value_Pull_Method_3_5 | DoD_Evan | He wants a new addition to his code, consecutive MCD and SD up to 5 total | Convert both codes, Methods 1, 2, 3, 4 to include 5 different peaks above average line | 2021-10-21 | 2021-10-21 | 0
1.9 | Thenar Muscles MEP Value Pull | MATLAB | MEP_Value_Pull_MEthod_3_6_Thenar MEP_Value_Pull_Thenar | DoD_Evan | Alternative code creation using non-averaged data | Within the Excel files provided - use the Thenar 1-10 columns of data instead of the averaged value column, need to do this for each column, for each method, for each participant. The way this should be layed out is Trials 1-10 (Rows), the current format for the columns. Teach Evan how to use structures to get his own data | 2021-10-27 | 2021-11-01 | 5
2 | Thenar Muscles MEP Value Pull | MATLAB | MEP_Value_Pull_MEthod_3_6_Thenar MEP_Value_Pull_Thenar | DoD_Evan | Updated MCD and SD values based on each Thenar Frame (1-10) There were several places that needed to be updated so that the end of the waveform wouldn't disrupt the structure, the common equations for MCD and SD were used in each code file | Need to go through and apply new MCD and SD equations to each of the Thenar Frames for each participant, output the data the same way | 2021-11-05 | 2021-11-05 | 0
2.1 | Thenar Muscles MEP Value Pull | MATLAB | MEP_Value_Pull_MEthod_3_6_Thenar MEP_Value_Pull_Thenar | DoD_Evan | MCD mean values were averaged including the fist value which was zero | Took out the zero value in the matrix and re-ran all codes | 2021-11-09 | 2021-11-09 | 0
2.2 | Create a Spike Script code file | Spike2 |  | Dod_Evan - yoga room | Code needs to be able to place a marker to create a window of when the muscles are active | Figure out how to trigger a vertical cursor to be placed during the G tick mark trigger Potentially set up a trigger through the Grass so one channel is only running when the grass is (kind of like the vertical cursor markers?) | 2021-11-09 | 2021-11-09 | 0
| Spike2 Data Recording | Spike2 | Pulse_Train and All_Electrode Configuration | Yoga Room Dod_Evan | Added channels to all_electrode configuration, IMP: Port connections are 1 less than the channel (channel 1 = port 0) If I plug the S1 Out from the Grass into a waveform port I can pick up on the signal, but to make things easier, I just put a REPORT code into the sequencer file | Need to write a Matlab script: IMP Digital Marker channel 32 is equal in time to channel 1, the indexes from channel 1 are equal to those of 3,5,7 - need to drop cursors for each of the three trials (6 total cursors) Keep the waveform channel | 2021-11-12 | 2021-11-15 | 3
| Spike2 Exporting Data | Spike2 | Pulse_Train and All_Electrode Configuration | Yoga Room Dod_Evan | When Exporting Spike2 Data Export as .mat file Uncheck the zero on time Export between cursors source non, source channel, waveform & times | Follow guidelines for exporting | 2021-11-13 | 2021-11-13 | 0
| Spike2 Exporting Data | Spike2 | Pulse Train and ALL_Electrode | Yoga Room Dod_Evan | File updated to also include Channel 15 such that a goniometer recording can be used as well. Cursors still need to be dropped Study Performed: 1. PRMR 2. Pendulum 3. Ankle 4. Flexor Withdrawal (Train Sequencer) 5. Flexor Signal | Evan’s study – Grass needs to be set to S1 Delay/ Output 1 for S1 ON; S1 Out plugs into 3 ADC input File also moved!! File moved to D:tss preliminary When adding a new veritcal cursor to the live streaming file, ATL 1 or ALT 2 drops them with labels 1 and 2 | 2021-12-03 | 2021-12-03 | 0
| Spike2 Exporting Data | Spike3 | Pulse Train and ALL_Electrode | NIH_TSS_Phase_1 | Created a New folder (name to the left) | All_Electrode_Channel file is located in new folder - is also different than the original because the S1 Out goes into channel 13 | 2021-12-14 | 2021-12-14 | 0
0
0
2 | TSS_Jasmine
2 | Data Analysis Initial Discussion | [5 empty] | 2021-09-01 | 2021-09-01 | 0
2.1 | Data Analysis Spike Code Locations and Discussion |  |  |  | Should be receiving Xsens trimmed files to put through existing Matlab code, [Dorsiflexion during walking] | Give output files to Jasmine Analysis Deadline Nov. 1st | 2021-09-13 | 2021-09-13 | 0
2.2 | Jasmine Code Files | Matlab | J_Codes | RMP | These files have the OLD code [Main_MVNX] | The Right/Left Extraction codes need to be updated to mesh with NEW version codes. Alterations need to be made for the naming - but code should run other than that | 2021-09-17 | 2021-09-27 | 10
2.3 | Jasmine Code Files | Matlab | J_Codes | RMP > Import_J_Data | Files all in the same folder. Need to update the main_mvnx file to load all data and organize into a structure. Updated for loops and structure within the document - issues with communication between old matlab load and old main for xsens data | Organize data into a structure such that all data can be loaded at once | 2021-10-01 | 2021-10-07 | 6
2.4 | Jasmine Code Files | Matlab | RMP | Data_Dorsi | Data given to Jasmine, In a 24 step cycle, 12 max dorsiflexion angles are reported for each R/L, data was organized vertically and adapted from Cazi old data files | IMP: Old Xsens files are used in accordance with the old load and main Xsens files - therefore to alter old files, calling the data, and data organization will be different | 2021-10-07 | 2021-10-07 | 0
2.5 | Jasmine Code Files | Matlab | RMP | Import_J_Data | The code currently shows cycles alternating in the beginning from TO to HS, this is incorrect - needs to always start at TO | Changed the Code to pull TO-HS every time so that the ankle data is being pulled for each swing phase of each middle 50% of steps IMP- for validation if code begins on HS, bypasses to next TO: this means the total number of steps differs every/other walk cycle I think | 2021-10-27 | 2021-10-27 | 0
2.5 | Ankle Code | Matlab | RMP/TSS_Ankle_1_12 | All files in this location for right now | Adjustments have been made on Cazmon's old files - originals can be found in Cazmon Desktop | Currently have added on to the original files SOL (L/R) and TA (L/R) usually in lines 52-58 for onset and 99-104 for Offset Using the parameters already set (very stringent - goes for 50+ points??? This gives us NaN and inf values - talk to Jasmine about this? | 2022-01-10
2.6
2.7
2.7 | [8 empty] | 0
2.8 | [8 empty] | 0
2.9 | [8 empty] | 0
3 | [8 empty] | 0
3.1 | [8 empty] | 0
3 | TMS_UE Jennifer
3 | Signal Filtering for Noise | Signal | 9_TMS Upper Extremity EMG Trial Data | (H) Drive | Trial 1: Using IIR Notch Butterworth Filter Trial 5: Using Band Stop |  | 2021-09-03 | 2021-09-08 | 5
3.1 | Filtering Literature Review | Jennifer File Sharing |  | One Drive | Key word Search: TMS, Filtering, Butterworth, EMG Signal Filtering | Conduct Lit Review, record findings: Neilson Data used sampling rate of 1000 - try to find reference material for filtering this | 2021-09-22 | 2021-09-24 | 2
3.2 | Filtering Literature Review | Jennifer File Sharing/Signal | One Drive_Signal Filtering for noise removal | EMG Trial Data;Tab [FIR_BP_TMSEMGfiltering_09282021] | Used BandPass FIR | Go through Neilson Data and record P-P differences | 2021-09-28 |  | -44467
3.3 | Device Pricing Information | Excel File/ Web | Device Pricing Spreadsheet | jg300416 | Pricing and specification information for the grip dynamometer | Asked for quote from Biometrics as well as information on one other device Find if there are additional devices / device sellers and quote information | 2021-11-05 | 2021-11-08 | 3
3.4
3.5
3.6
3.7
3.8
3.9
4 | [8 empty] | 0
4.1 | [8 empty] | 0
4.2 | [8 empty] | 0
4.3 | [8 empty] | 0
4 | SCIMS_Nick
4 | Meeting to discuss SCIMS relative Motion Plots | Matlab | ACC_Data Relative motion plots |  | Wants a way to categorize and group data plots, the paper sent (in SCIMS folder) shows an SSD equation that is customized to see the differences between each plot | Determine how to incorporate this equation, move each person into different centroids, categorize participants into different groups (Day1 and Day 5). What differences can be seen between each gait cycle [Cazmon job] | 2021-09-28 | 2021-09-28 | 0
4.1 | SCIMS | Matlab |  |  | Left_Extraction this file is located in the main RMP folder - this file interfaces with the old load Xsens data file | Load Xsens file should use the segment and joint files as well | 2021-12-16 | 2021-12-16 | 0
0.1 | [8 empty] | 0
4.3
5 | Matlab App Designer/Lab Equipment Management
| Xsens App Development | Matlab | Xsens_APP_V2 | RMP Folder | Presented the Code in lab meeting, Notes: Add - Relative Motion Plots [Hip vs. Knee] - Plot the Left, Hip/Knee/Ankle [ joint on the y, time on the x] with ability to switch x,y,z - Total Excursion over time - Threshold angles - Participant Overlay graphs, able to visual multiple angles on one graph or multiple trials on one graph - Recruitment Curves - ACC visual - Possiblity of creation of seperate Signal Application as well | How can I toggle it such that you can select X, Y, Z on/off or select specific joint angles on/off | 2021-10-21 |  | -44490
| Xsens App Development | Matlab | Xsens_APP_V3 | RMP Folder | Updates to the app | Switch over the code to the new data tree The multiselect option does not work for the checkbox tree - because of this limitation, we should leave it as it currently is, maybe add to it in the future | 2021-11-01 |  | -44501
| The Pinchmeter stopped working | Pinchmeter | N/A Yoga Room | N/a | The cord for the pinchmeter became severed - this led to the spike channle to show a signal that was at +/- above zero with a diaganol downward slope as if it is plugged into nothing. The new wiring is printed out and is also displayed on the current cable | Wiring is as shown in the goniometer user manual | 2021-11-10 | 2021-11-10 | 0
| Motion Lab BackPack Box has two ports that are reeiving signal but jamming when the EMG cord is pulled out | Motion Lab Backpack |  |  | If you go down to central supply (by the cafeteria) they will have you fill out a form to get it shipped out with the tracking information tagged to your emial | Things you need: Account number 28014 Address/buisness phone #/ iinsurance ammount | 2021-11-10 | 2021-11-10 | 0
| Manage the location of equipment and software user manuals |  |  | S:\CLIN_REA\Hulse Lab\Equipment and Software | Shortcut on Desktop | Make sure this folder stay up to date with current device manuals and user guides. Additional resource for user manuals is bottom drawer of the desk | 2021-11-30 | 2021-11-30 | 0
| Creation of Standard of Operations (SOP) | Word Document |  | H:\Standard Of Operations | How software/lab tech works and should be set up | Continuous work in Progress | 2021-12-03 |  | -44533
| Grip Dynamomter Set Up | Command Echo Grip Dynamometer |  | H:\Standard Of Operations | Received grip dynamometer - contains a factory default calibration - elctrical load cells allow for this to be reliable. Additional calibration measure can be weight suspension using the yellow cable provided | Need to find a weight that has a hole in the middle (bar weights) such that it can be suspended. Remember by wrapping the cable it will change the force characteristics so only place the cable around the center of the handle | 2021-12-09 | 2021-12-09 | 0
| OLD Matlab Documents | MATLAB/Other | Cazmon Desktop | On Desktop but also on S drive | Folder contains all old files that Cazmon previously had - additional files from Nick's study also in there (Cazmon mentions everything is "done" I'm not sure what he is refering to here | If there are issues with old Xsens codes it is because these files use the old Xsens Load code which has since been updated | 2021-12-17
0
0
6 | TRNS_Anastasia
| Note Recording for Study | Signal/Spike/PEST |  |  | Meeting Discussion: How to record notes, nomenclature | Take a look at wave forms to distinguish between MEP and non-MEP, Look at emails sent by Jennifer and Anastasia - take a look at info | 2021-09-22 | 2021-10-04 | 12
| Study Visual check of MEP | Signal/Spike/PEST | P09-11OCT2021 | studies>CHNRF_tRNS>P09 | Look at signal MEP Y/N | Make a meeting with Anastasia to go over signals | 2021-10-11 | 2021-10-12 | 1
| Meet with Cazmon regarding Script Bar button operations | Signal | Yoga Room computers - signal subtraction and 2kHz | Yoga room CHRNF | Script Bar Button malfunction - will not show appropriate log view of L/R data | Set up meeting with Cazmon | 2021-10-14 | 2021-10-14 | 0
| Data Collections button fixes | Signal | Yoga Room computers - signal subtraction [drag] and 2kHz [button] | Yoga Room CHRNF | Location of button operations and drag - just reset the program if something seems to bug out | Select CHNF button, hit start and ok, then move forward, open log window Drag in file, [Subtraction], then run from script | 2021-10-20 | 2021-10-20 | 0
| Fixing the pinching dynamometer | Electronic dynamometer | N/A Yoga Room | Yoga Room | Dynamometer was unplugged with one of the outlets twisted when I came downstairs for the set up process | The cable was soldered by George that goes from the dyanmometer into the motion lab box system. | 2021-11-10 | 2021-11-10 | 0
| Pinch dynamometer | Electrononic dynamomter | N/A Yoga Room | N/A Yoga Room | Pinch Meter repair kit now located in Yoga Room | With small force windows (under 1) the pinch dynamometer seems to have a bit of drift - try calibration in-session window before adding processing to the channel. Then place a horizontal cursor on the screen to mark starting force level so that you can see throughout testing if it is fluctuating significantly | 2021-12-09 | 2021-12-09 | 0
0
0
0
0
0
7 | Professional Development
| Engineering Project Management | [5 empty] | 2021-08-16 | 2021-09-20 | 35
| Course 1: Initiating and Planning | [5 empty] | 2021-08-16 | 2021-08-30 | 14
| Course 2: Scope, Time, and Cost | [5 empty] | 2021-08-30 | 2021-09-20 | 21
| Course 3: Risk, Quality, Teams, and Procuremnt | [5 empty] | 2021-09-13 | 2021-09-20 | 7
| FE Exam |  |  |  |  | Begin studying | 2021-09-20 |  | -44459
| Softball Journal Article |  |  |  |  | Go through the email sent with corrections - read through suggested articles | 2021-10-25 |  | -44494
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0