## 2021
Task Manager | [9 empty] | Notes: ADD Major Project milestones to Project Portfolio
Jessica Gilliam
| Time (Week) | Project Type | Critical Issues | File Path Location | Resolved | To Do | Tasks Completed | Major Project Milestones |  | TouchPoint Goal | Employee Comments | Development Goals | Update
| 6/21 - 6/25 | DoD_Evan | Thenar muscle output Needed Excel output page needed |  | √ | N/A | Data Exported to Evan 6/24 | N/A | 2021-08-12 | Become proficient in Spike and Signal Software such that I am able to self-sufficiently use each platform. | Spike and Signal are each used in the lab during data collection. By becoming self-sufficient with the use of these platforms, I will be better equipped to independently work on lab research studies. | 1. To take a course such that my own personal coding or buisness srelation skills improve 2. To build and improve professional relationships here at Shepherd Center
|  | Xsens Dot | Learning Documents Establish app configuration (1.60 Firmware Update) Firmware Update Failure |  | √ | N/A | (IOS) App installed | N/A | 2021-08-13 | To take a professional development course that will improve job proficiency and ability. | The goal is to use the employee academic stipend to be used towards a professional development course. This course could be code, software, or business related. |  | Enrolled in yearly subscription for coursera (8/17) * This needs to be canceled unless you want to continue this for another year
| 6/28 - 7/2 | Xsens Dot | Charging (battery < 25%) Fade in/out, 1-second cycle Contacting Xsens Support |  | √ | Identified issue - Xsens Dot Sensors are not holding charge independently | Contacted Xsens Support: Package for Xsens Dot Replacement to be shipped (Approx. Arrival 2 weeks) | N/A | 2021-08-14 | Proficiency in lab data collection and processes. | As a new employee I need to become familiar with the processes of human subject data collection for the Hulse Research Lab
|  | VETA Matlab Code | Convert_Signal_Veta>FindEMG>VisualizeEMG Understand File Path |  | √ | Look at FindEMG file | Understanding of File Path | N/A
|  |  | Time offset, not taking baseline into account |  | √ | Make adjustment to artefact code lines [182-280] Try to Change Artefact | N/A | N/A
|  |  | Channel Visual is not showing all 6 channels |  | √ |  | Altered VETA Visualize_EMG code to create 6 Channel image | N/A
|  |  | Image does not save, only saves data in an output table with which trials have been accepted |  | √ | Ask Cazmon whether this is something we need or if it is beneficial to leave it this way | Jennifer confirmed that visual was less IMP | N/A
|  |  | Channel Visual will not show MEP on channels 5 or 6 When selecting MEP [1 2 3 4 5 6 ] an error occurs on visualizeEMG code |  | √ | Alter VisualizeEMG code so that MEP can be shown on each channel. Could there be a way to alterincoming Signal data so that the first 4 channels are the ones that need the MEP data? | Resolved: Exporting Data in pairs of 4 only | N/A
|  | Kinovea Software | Validation & Repeatability of the free opensource software |  | √ | Find resources to confirm assumptions of reliability | Found two journal articles - both of which show previous studies conducted with software - shared this information with Nick | N/A
| 7/5 - 7/9 | VETA Matlab Code | No artefact Channel: this causes issues with the calculation of every other variable |  | √ | Meeting on Friday (7/9) 9:30AM to create an artificial artefact channel | Aretfact Code Created | N/A
|  | Xsens Dot | When is the shippment getting in? |  | √ | Check to see when this will be delivered | Delivered the week of 7/12 or later | N/A
|  | VETA_APP Creation | VisualEMG was created from an old Guided App builder, Current application builder is call AppDesigner. Need to create an App that will load in data files, create visual output with UI buttons |  | √ | Load data into GUI Create Functions for displaying visual graphs Determine how to highlight section of graph - with button color changes, look at old graph from Dr. Oliver paper | Created 6 visual graph plots with Artefact, Onset, Offset clearly defined | Creation of VETA APP This App has the ability to plot 6 different recorded signal channels and visual show Artefact, MEP Onset, & MEP Offset
|  |  | EMG signals are being over written |  | √ | Look at Graph_APP lines 68 - 135 to fix overwrite | All graphs plot without over write
|  |  | App Designer compiler |  | √ | Need to compile app into web based app | App Compiled
|  | XSENS_LOAD_App Creation | Create an App for an non-MATLAB user to load MVN data, analyze data, output signal variables, GUI interface |  | √ | Load in values from data tree - check structure, load left and right extraction | Codes lines created for loading structures | N/A
|  |  | Resolve Load_MVNX issue |  | √ | Used the XSENS originial files stored on C:\\Programs\Xsens\DeveloperTools | Downloaded Current Developer Tools | N/A
|  |  | Naming Mechanisms are inaccurate |  | √ | Change Segment Position Code and Joint Angle Code to match pulled data from Main_MVNX | Changed Segment & Angle import | N/A
| 7/12 - 7/16 | XSENS_LOAD_App Creation (RMP) | Check that data is being pulled accurately from main |  | √ | Order of execution should be main>joint_angle>cycle>L+R Extraction |  | N/A
|  |  | Push Button opporation not performing |  | √ | Youtube Videos for App Designer have been helpful in the past - maybe take a look at these again | Combined each code for Xsens import into app | N/A
N/A
|  | TRNS (Anastasia) | Take notes on how to perform collection alone |  | √ | Three Step outline notes for testing on Monday next week | N/A | N/A
|  | Dod_Evan | Pre_Thenar Created, Evan Needs to Validate |  |  | Go through the same process for Post_Thenar |  | N/A
|  |  | Evan wants to change the code from 5 Consecutive data points to 3 consecutive to see if that minimizes NaN values |  | √ | Change 4 lines, if statements list this out, Git Hub code change 7/14 | N/A | N/A
|  | Jasmine | Schedule meeting to discuss data output |  | √ | Ask about output values | N/A | N/A
|  |  | Can use Xsens app and tweek it for Jasmine |  | √ | Make changes: right and left joint ankle visual with max dorsiflexion(z) and range of motion durng volitional tasks |  | Creation of XSENS_APP_Jas This app has the ability to plot L/R ankle angle, find dorsiflexion and voliton ROM values and export into an Excel file
|  | XSENS_LOAD_App Creation_UPDATE (RMP) | App does not display enough information. Needs the ability to export as well |  | √ | Create multiple data display windows. These include participant number, session number, Left and right graphs with data of hip(x) and knee(y) and the ability to export | N/A | N/A
|  |  | Work on Exporting Data |  | √ | Excel? .m file? |  | Creation of XSENS_App This app has the ability to plot R/L Hip Angle(x) and R/L Knee Angle(y) Able to Batch process and pull in lots of data files, Ability to Export two excel files (joint Data and Segment Data)
| 7/19 - 7/23 | MATLAB License | Talk to Cazmon about cost analysis for Matlab license and app designer toolbox |  | √ | Create a cost report and give this to Jennifer (2-3 weeks) | N/A | N/A
|  | XSENS_APP_Jas | Find out what volitional range of motion she is looking for |  | √ | create a calculation and display on EditField, adjustment to export - make sure values calculated get exported as well | N/A | N/A
|  |  | Change App to export only and batch process specific file types |  | √ | change so that it runs through all 11 participants and exports calculated data vlules only | N/A | N/A
|  |  | Run File |  | √ | Run entire import file and view exported Excel Change code layout to batch code layout Run and save documents - send to Cazmon | Unneccessary as an APP - altered to just a code file Xsens_Jas | Creation of Xsens script file - Volitional Range of motion and maximum dorisflexion of the L/R ankles - located RMP>Xsens_Jas
|  | XSENS Main APP | Alter main code layout |  | √ | Want to change this so that you can choose which participant to load in | Changed so that the data can be loaded in as a folder or multi selcted files | N/A
|  |  | Update tree structure |  | √ | Alter data analysis section such that the tree structure leads to an internal code change - We want to select an item and display value? Prompt?graph? | Tree structure allows for user to find what they need without unneccessary prompts in the command window | N/A
|  |  | Update Export to allow all files to be exported |  |  | Export only does one file type export currently - needs to be changed | N/A | N/A
| 7/26 - 7/30 | XSENS Main APP | Issues with pop-up window plotting graphs and displaying table data |  | √ | adjust pop up - look to see if it will work on its own in command window before changing code | N/A | N/A
|  |  | Start to incorporate walking data |  | √ | Cazmon - code (create helper functions) | N/A | N/A
|  |  | Walking Data Nodes |  | √ | Shorten nodes and display HS/TO - graphical? Data view in Table? | N/A | N/A
|  |  | Will not index participant number, only order of import |  | √ | Need to change this prompt such that it searches for participant ID number | N/A | N/A
|  |  | When User is typing in participant ID change this |  | √ | User should be able to select which file to use from drop down menu | Creation of Drop down menu | N/A
|  |  | File pop up takes too long when visually assessing the data |  | √ | Need to make it so that the graphs can cycle through - can possibly change this such that there is an external app that pops up, maybe embed the graphs into the display so that you can see x,y,z | Creation of multiple buttons to execute analysis on graph that is preferred | N/A
| 8/2 - 8/6 | XSENS Main APP | Next need to work on export?? Walking data?? |  | √ | Need to talk to Cazmon about next steps on this | Did as much as we can so far, need to wait for feedback to continue on this project | N/A
|  | Function - MEP Finder | Work on creating new function |  | √ | Create a new functiont that finds a pattern within a waveform, info in Matlab function created within the Veta Folder | Initial function created | N/A
[5 empty] | √ | Function gives an array of length n, need to find the equivalent EMG_sec value to the true logical statement outputs | creates output of the Onset time and Index now | Creation of MEP_finder: this finder allows for the user to find locations within the code of where an MEP is located, Lists out the result as a matrix with MEP_Onset_index and time
|  | Creation of lab email and Icloud |  |  | √ |  | N/A | Lab Email & iCloud: hulseresearchlab@gmail.com Shepherdlab2020
|  | Android Studio | Begin youtube tutorials on app creation |  | √ | Xsens has an SDK app for android tutorial - look at creating your own dummy app | Android APP is very similar to the way MATLAB APP is layed out - beneficial for language purposes | N/A
|  |  | How do I merge the XSENS SDK with the android app? |  | √ | Look at youtube import external sdk into android studio, look at ability to export matlab apps to SDK?? Is this useful?? | N/A | N/A
|  |  | Issue with HAXM requirement to run app HAXM - Hardware Accelerated Execution Manager: helps to speed up and improve performance |  | √ | Issue with downloading - potential fixes within BIOS or system control | N/A | N/A
|  | MATLAB License |  |  | √ | Should be receiving a quote later this week | N/A | N/A
| 8/9-8/13 | MATLAB License | License has been sent via email -need to send an email to Edee about service request for software |  | √ | Send email to Edee about invoice & Service request | N/A | N/A
|  | Android Studio |  |  | √ | What do we want the app to accomplish - is it necessary to start from ground zero (bluetooth connection?) to build something that already works? We will have to code angle adjustments regardless of writing it in the app before or after | N/A | N/A
|  | KineXYZ |  |  | √ | This might be the solution we are looking for. Allows you to calibrate, build model, and build live feed of angles/accelerations etc. How do we export data? Is there a way to live stream data? | N/A | N/A
|  | Xense_Jas | Validation Process - different numbers seen |  |  | Cross Examine the different numbers seen for the validation process | N/A | N/A
|  | CON_finder | Look at creating less input functions such that it runs without difficulty, define user input later on inside the function |  | √ | User input and output nan values | I was able to alter this code such that there are output nan matrix if the conseutive solver does not find anything of value. Need to further develop POI | Creation of MEP_finder --> New Name CON_Finder for consecutive finder. Ability to use optional function commands to further define what you are trying to find
|  |  | Development of POI |  | √ | I need to further develop POI such that if the number 1- n is user selected, the report will list POI 1:n of that number, have this prior to MEP_onset in both cases so that if POI is selected then it allows for a return of only a few numbers | N/A | N/A
| 8/16-8/20 | MATLAB License | Activation Key |  | √ | Matlab License Installed and up to date will all code information | N/A | N/A
|  | VETA | Looked through document Jennifer sent me |  | √ | Updated the license on laptop to include necessary toolboxes to run the code | N/A | N/A
|  | Goals | Meeting with Edee to discuss touch point goals |  | √ | Updated goals to be a bit more specific | N/A | N/A
|  | Enrolled in Coursera Course | Meet with Edee Copy of invoice Website link of purchase |  | √ | 8/17 (1 year of unlimited classes and certificate opportunities) | N/A | N/A
|  | Signal Sequencer File | Create a sequencer file in signal - Must contain 5 repeating stimulants each (1 every .5 seconds) - Trigger the unit for spike display |  | √ | Read through Signal functions and generate new code | N/A | N/A
| 8/23-8/27 | Signal Sequencer File | Preliminary code created | Yoga room computers > Dod_Evan > Pulse_5 | √ | Need to update the hardware such that there are inputs and outputs to the grass, then try to run it using the volt meter/oscilliscope |  | N/A
|  | EPM Course work Week 3 |  |  | √ | Work through end of week assignment | N/A | N/A
|  | Interviews | Pick a winner | N/A | √ | ** After interview tomorrow put together a google doc and print to let edee know what who your choice is
| 8/30 - 8/3 | EPM Course 2 started 8/30 |  |  |  | Work through week 1 of the course
|  | Signal Sequencer File |  |  |  | Try out new set up, see if it will work with pulses
** Sign up for remote day on the 15th